## Sheet1
Actual project time "month" | 10000/160*5 | 12.5
Project is overbudget by 1500
Project is delayed by
Time"month" | Actual Cost | Earned Value | Planned Value
0 | 0 | 0 | 0
7 | 7000 | 5500 | 5000
12 |  |  | 10000